This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
   Select "Completed Day 1" if finished on the first day, and
   similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product_Backlog
Product Name:	MICE Manager					Complete Fields in Green!!!
Team ID:	Bruno Technologies

	Team Member Name					Initials	Student ID
Required	Joseph Brewster					JB	1001049436
Required	Emily Knowles					EK	1001250974

	Note: Teams MUST be approved by the Professor (NOT TA) in advance

Sprint #	Remaining	Completed This Sprint			Comment
0	37			Total	Total number of features (in column H)
1	33	4		1	Total features left at the end of Sprint #1
2	33	0		2	Total features left at the end of Sprint #2
3	33	0		3	...and so on
4	33	0
5	33	0
6	33	0

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new ice cream flavor	Stock and sell dairy products	picture not yet required, just test the classes here w/o GUI
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new container	Stock and sell dairy products	Picture not yet required
CT	3	1	5	1	Finished in Sprint 1	Manager	Create a new topping	Stock and sell better dairy products	Picture not yet required
GUI	4	1	8	1	Finished in Sprint 1	Manager	Use a GUI instead of a terminal	Reduce training costs	This is the main window, with menu bar, tool bar, and optionally status bar
IGUI	5	2	13	2		Manager	Use dialogs to create items	Reduce training costs	One dialog should server for all items with minor variations
CS	6	2	8	2		Server	Create a serving of ice cream in a container with toppings	Create dairy products to sell	Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and push on a vector
PS	7	2	5	2		Customer	Show the components of a serving (container, scoops, and toppings) for verification	Ensure my order was taken correctly	This is effectively a to_string method to a dialog with confirm or start over buttons
CTM	8	2	3	2		Manager	Create a new server	Staff the emporium
CB	9	2	2	2		Server	Create a new beloved customer	Keep track of our customers
CO	10	2	13	2		Server	Create an order of many servings of ice cream	Serve everyone in a customer party
CSB	11	2	1	2		Customer	Create a serving of ice cream in a container with toppings	Self-order and not have to deal with people	This just enables the Customer role to do what the Server can do in defining a serving…
COB	12	2	1	2		Customer	Create an order of many servings of ice cream	Self-order and not have to deal with people	...and order
CE	13	3	5			Manager	Create an emporium that stocks items and maintains a cash register	Manage the emporium	This includes item stocks, server and customer lists, and the cash register
MST	14	3	8			Manager	Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled)	Ensure each order is filled and payment collected
SAVD	15	3	8			Manager	Save all data to a default file	Ensure our data isn’t lost
LOAD	16	3	5			Manager	Load data from a default file	Ensure our data isn’t lost
POS	17	3	5			Server	Show the servings in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC	18	3	5			Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
CM	19	3	3			Owner	Create a named manager	Delegate management tasks to a pro
P&L	20	4	8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy
RI	21	4	5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers
PIX	22	4	21			Customer	Add and display pictures for each item (container, ice cream flavor, and topping)	Better understand the menu
RTM	23	4	8			Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members
ETMS	24	4	8			Manager	Change a server salary	Offer promotions and pay bumps to motivate our team members
AI	25	5	8			Server	Restock items (ice cream flavor, container, and topping)	Ensure we can fill every order
RO	26	5	8			Manager	Create an Order Report, showing all pending orders (unfilled and filled but unpaid)	Better manage our production process
RB	27	6	5			Manager	Display a Customer Report, listing all info about each customer	Better attract repeat customers and handle complaints
EF	28	6	8			Manager	Edit an ice cream flavor	Improve our data and keep it synced to reality
EC	29	6	8			Manager	Edit a container	Improve our data and keep it synced to reality
ET	30	6	8			Manager	Edit a new topping	Improve our data and keep it synced to reality
ROA	31		3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
SALL	32		5			Owner	Save all data to a specified file	Franchise my company
LALL	33		5			Owner	Load data from a specified file	Franchise my company
CENEW	34		13			Owner	Create a new franchise	Franchise my company
XI	35		21			Manager	Retire an item (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
XT	36		13			Manager	Suspend a server (no longer allow their selection for an order or restock, but keep in reports)	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	37		5			Manager	Restore a server	Add a former team member tack into service
Product Backlog Burn Chart
Features Remaining at end of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 19		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 26
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	4	0
Day 2 Left	4	0
Day 3 Left	4	0
Day 4 Left	4	0
Day 5 Left	4	0
Day 6 Left	0	4
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CF	JB	Create Ice Cream Flavor	Completed Day 6
2	CC	EK	Create Ice Cream Container	Completed Day 6
3	CT	JB	Create Ice Cream Topping	Completed Day 6
4	GUI	EK	Create GUI	Completed Day 6
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 26		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 02
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	8
Day 1 Left	8	0
Day 2 Left	8	0
Day 3 Left	8	0
Day 4 Left	8	0
Day 5 Left	7	1
Day 6 Left	7	0
Day 7 Left	7	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	IGUI	EK	use dialogs to add items	Completed Day 5	manager
2	CS	JB	create serving of ice cream	In Work	server
3	PS	EK	show components of serving		customer
4	CTM	EK	create new server		manager
5	CB	EK	create customer		server
6	CO	JB	create order of servings	In Work	server
7	CSB	JB	create a serving of ice cream	In Work	customer
8	COB	JB	create order of servings		customer
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_03_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 02		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 09
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_04_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 09		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 16
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_05_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 16		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 23
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_06_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 23		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 30
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days